## Project Planner
Hybrid model of Bi-LSTM and CNN for Multivariate Time Series Classification for ecommerce sales Forecasting
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 11 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Research Topic Submission | 1 | 3 | 2 | 3 | 100%
Research Proposal Submission | 4 | 6 | 5 | 6 | 100%
Literature Search | 10 | 2 | 11 | 1 | 50%
Literature Review | 12 | 2 | 0 | 0 | 0%
Data Collection, Preprocessing | 14 | 1 | 0 | 0 | 0%
Integration of BiLSTM and CNN algorithms | 15 | 2 | 0 | 0 | 0%
Implementation of the hybrid model | 17 | 2 | 0 | 0 | 0%
Train the integrated Model | 19 | 1 | 0 | 0 | 0%
Validate & Evaluate the model | 20 | 1 | 0 | 0 | 0%
Mid Thesis Submission | 21 | 1
Review Statististical Tests | 22 | 1 | 0 | 0 | 0%
Compare with other models | 23 | 1 | 0 | 0 | 0%
Presentation & Final Thesis Submission | 24 | 1 | 0 | 0 | 0%